ACROSS THE AISLE

EVENT CREATION TIMELINE

- Pick a date for first (and second?) event and check for university conflicts.

  - DUE DATE: 
(Start planning about 1 month before event)

- Reserve a room for the events.

  - DUE DATE:
(Start planning about 1 month before event)

- Select a controversial, relevant, narrow topic for each event.

  - DUE DATE:
(Start planning about 1 month before event)

- Ask a professor to be a guest speaker.

  - DUE DATE:
(Start planning about 1 month before event)

- Compile a list of subtopic ideas.

  - DUE DATE:
(Decide subtopics about 4 weeks before event)

- Decide subtopics. After discussion, send subtopics to Advisor for review.

  - DUE DATE:
(Meet about 4 weeks before event)

- Finalize subtopics. Assign ATA team members to draft subtopic paragraphs.

  - DUE DATE:
(Finalize and assign about 3 weeks before event)

- Create advertisements for event (mass email, digital ad, physical flyers, tabling, etc.)

  - DUE DATE:
(Create 1.5 to 2 weeks before the event)

- Send out Qualtrics survey with subtopic questions to event participants.

  - DUE DATE:
(Send out 1.5 weeks before the event)

- Send One Pager drafts to Advisor for review.

  - DUE DATE:
(Send drafts about 10 days before the event)

- Send out a "Last Day" reminder to event participants to take Qualtrics survey.

  - DUE DATE:
(Send day before closing survey)

- Close survey. Select responses to add to One Pagers.

  - DUE DATE:
(Close 4-5 days before the event)

- Count approximate attendees for food order. Place food order.

  - DUE DATE:
(Order food 4-5 days before the event)

- Send a copy to the guest presenter to review/edit. Print One Pagers.

  - DUE DATE:
(Send 1 day before the event)

- Write a thank you card and get chocolates/flowers for the guest speaker.

  - DUE DATE:
(Purchase at least 1 day before the event)

- Pick up food. Eat the food. Have a great event!

  - DUE DATE:
(Day of the event)